## Sheet1
Description | Start Date | Durations
Field Visit of Na:pukhu Mini Mart | 2016-05-10 | 2
Requirement Analysis | 2016-05-12 | 4
Design Phase | 2016-05-17 | 12
Development Phase | 2016-06-01 | 25
Implementation Phase | 2016-06-26 | 14
Debugging and Maintenance | 2016-07-11 | 25